## 2024 ATC Bay Space(Shakedown)
ATC Shakedown Bays/FTE Forecasting (1 Truck = 1 Bay) |  |  |  | January (2024) |  |  |  |  | February (2024) |  |  |  | March (2024) |  |  |  | April (2024) |  |  |  |  | May (2024) |  |  |  | June (2024) |  |  |  | July (2024) |  |  |  |  | August (2024) |  |  |  | September (2024) |  |  |  |  | October (2024) |  |  |  | November (2024) |  |  |  | December (2024)
Program | LG1 | LG2 | Proj Description | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-05-17 | 2024-05-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30
E82 (Cooper Young) | [17 empty] | 1 | 1
[14 empty] | 1 | 1
[20 empty] | 1 | 1 |  |  |  | 1 | 1
1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
[25 empty] | 1 | 1
H06 (Andrew Vara) | [24 empty] | 1 | 1 | 1 | 1 | 1
[25 empty] | 1 | 1 | 1 | 1 | 1
[22 empty] | 1 | 1 | 1
[17 empty] | 1 | 1 |  |  |  | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 |  |  |  | 1 | 1 | 1 | 1
[18 empty] | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1
H08 (Prashant)
[9 empty] | 1 | [7 empty] | 1 | 1
1
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
[13 empty] | 1 | 1 | 1 | 1 | 1
[19 empty] | 1 | 1 | 1 | 1 | 1
[9 empty] | 1 | 1 | 1 | 1 | 1
[9 empty] | 1 | 1 | 1 | 1 | 1
[22 empty] | 1 | 1 | 1 | 1 | 1
[22 empty] | 1 | 1 | 1 | 1 | 1
[17 empty] | 1 | 1 | 1 | 1 | 1
[15 empty] | 1 | 1 | 1 | 1 | 1
[19 empty] | 1 | 1 | 1 | 1 | 1
[14 empty] | 1 | 1 | 1 | 1 | 1
[23 empty] | 1 | 1 | 1
J01 (TBD)
J07 (Bushan Deshmukh) |  |  |  |  | 1 | 1
[5 empty] | 1 | 1
[30 empty] | 1 | 1
[28 empty] | 1 | 1 | [10 empty] | 1 | 1
[28 empty] | 1 | 1 |  |  |  | 1 | 1
[36 empty] | 1 | 1
1
J08 (Abraham Casanova)
[10 empty] | 1 | 1
[14 empty] | 1 | 1 | 1
[15 empty] | 1 | 1 | 1
[16 empty] | 1 | 1 | 1 | 1
[16 empty] | 1 | 1 | 1 | 1
[16 empty] | 1 | 1 | 1 | 1
[34 empty] | 1 | 1
[33 empty] | 1 | 1
[34 empty] | 1 | 1
[33 empty] | 1 | 1 | 1
[33 empty] | 1 | 1
[45 empty] | 1 | 1
[34 empty] | 1 | 1 | 1
[33 empty] | 1 | 1
[34 empty] | 1 | 1
[34 empty] | 1 | 1 | [7 empty] | 1 | 1
[33 empty] | 1 | 1 | 1
[34 empty] | 1 | 1
[35 empty] | 1 | 1 | [8 empty] | 1 | 1
[35 empty] | 1 | 1 | [8 empty] | 1 | 1
[34 empty] | 1 | 1
[34 empty] | 1 | 1 | [7 empty] | 1 | 1
[34 empty] | 1 | 1 | [7 empty] | 1 | 1
[43 empty] | 1 | 1
[34 empty] | 1 | 1 | [7 empty] | 1 | 1
[41 empty] | 1 | 1 |  |  | 1 | 1
[34 empty] | 1 | 1 | [5 empty] | 1 | 1
[41 empty] | 1 | 1 |  |  | 1 | 1
[35 empty] | 1 | 1 | [8 empty] | 1 | 1
[33 empty] | 1 | 1
[34 empty] | 1 | 1 | [7 empty] | 1 | 1
[45 empty] | 1 | 1
J09
[33 empty] | 1 | 1
[41 empty] | 1 | 1
[41 empty] | 1 | 1
[41 empty] | 1 | 1
[41 empty] | 1 | 1
[48 empty] | 1 | 1
[48 empty] | 1 | 1
[48 empty] | 1 | 1
[48 empty] | 1 | 1
s26
|  |  | ATC Bays (1 Truck = 1 Bay = One Tech) | 0 | 5 | 5 | 3 | 3 | 7 | 6 | 5 | 2 | 3 | 4 | 6 | 8 | 11 | 11 | 9 | 4 | 5 | 7 | 8 | 7 | 21 | 18 | 3 | 5 | 6 | 1 | 1 | 0 | 8 | 20 | 17 | 5 | 1 | 0 | 0 | 1 | 8 | 7 | 6 | 6 | 7 | 7 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Shakedown Hours Per Master Build Operations | 0 | 200 | 200 | 120 | 120 | 280 | 240 | 200 | 80 | 120 | 160 | 240 | 320 | 440 | 440 | 360 | 160 | 200 | 280 | 320 | 280 | 840 | 720 | 120 | 200 | 240 | 40 | 40 | 0 | 320 | 800 | 680 | 200 | 40 | 0 | 0 | 40 | 320 | 280 | 240 | 240 | 280 | 280 | 0 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Totals | Jan | Feb | Mar | Apr | May | June | July | August | September | October | November | December
|  |  |  | Shakedown Man Hours Per Month | 640 | 800 | 840 | 1600 | 1720 | 1280 | 1200 | 920 | 880 | 800 | 320 | 0
|  |  |  | Totals | Jan | Feb | Mar | Apr | May | June | July | August | September | October | November | December
|  |  |  | Average Bays Per Month for Shakedown | 3.2 | 5 | 5.25 | 8 | 10.75 | 8 | 6 | 5.75 | 4.4 | 5 | 2 | 0 |  |  | H06 requires two personnel per vehicle | H08 requires 5 personnel
|  |  |  | Totals | Jan | Feb | Mar | Apr | May | June | July | August | September | October | November | December
|  |  |  | Engineers Required | 3.2 | 5 | 7 | 8 | 10.75 | 8 | 6 | 5.75 | 4.4 | 5 | 2 | 0
Note - Shakedown hours per vehile with one engineer per bay